## Slide 1: HCL Due Diligence
23 February 2018

## Slide 2: Agenda
Priority items for discussion
  Exec Update (Piers / Stuart)
Status Reports against Plan
  Due Diligence, Resource Augmentation, Model Solution (HCL - this pack)
  Due Diligence (TP)
  Legal & Commercial (TP)
  People & HR (TP)
  Communications (TP)
AOB

## Slide 3: Workstreams
We need to form a view on each of the following workstreams:-
Programme Management Stephen/ Stevan
Overall architecture Kottai/ Maurice
Business Process design Kottai/ Maurice
Solution design Kottai/ Maurice
Integration architecture Sanjay
Data architecture/ migration Sanjay/ Suresh
Testing Suresh
Service Design/ Transition Amit
Deployment Approach/ Release 2 Stephen/Stevan
In preparation for next week’s workshop, please complete the attached template for your respective areas.

## Slide 4: People we have met
Rosemary Bell
Cari Spokes
Simon Doyle
Chris Stone
Riaz Khan
Mark Griffiths
David Golding
Pascal Cosnucau
James Weller
Nick Ingram
Michael Kennedy
Cut over team
Workstream: __CM___

## Slide 5: Views so far
Strengths, examples of good practice
Good use of internal process within teams
Centralised Teams IT teams have decent interaction and centralised Change Management Process
Individuals within teams knowledgeable
Areas for concern
Document Management (Poor)
Requirements Management (Poor)
Defect Management (Dispirited)
QA Management (None)
Reliance on Spreadsheets and manual updates
Silo Inundated Project
No Effective Cross Workstream Interaction
No Project Tool Rationalisation
Poor cross project communication
Next Milestone driven approach
Workstream: __CM____

## Slide 6: Suggestions
Project Management Tool (Jira)
Centralised tool for lifecycle and task management (including defects and requirements)
Centralised Reporting and Customisable Dashboarding
Ideal for cross workstream and agile based projects
Multipurpose use (From Development tracking to PMO staff onboarding).
Already used in TP dev teams outside of Momentum
Cheap user licensing
GAPS
Quality Manager
Requirements Manager
Defect Manager
Workstream: __CM____

## Slide 7: Exam Questions - 2
What activities are on the critical path to go live in October?
  Shortage of Environments prohibits any further system integration testing post SIT. This prevents effective verification of fixed defects.
  No clear definition of requirements
  No clear definition of standards and Quality Assurance across workstreams
  Complex Infrastructure with heavy reliance on Universe infrastructure that isn’t clearly tracked
  No Decommissioning Workstream for Heritage Applications (Risk due to cross pollination of apps across brands).
What are the critical success factors to achieving these on the current schedule?
  Establishment of additional ‘integrated’ environments
  Establishment of Requirements traceability matrices for each workstream
  Establishment of a Quality Manager and publication of required standards
  Establishment of a Decommissioning workstream operating under change control protocols
Workstream: _______

## Slide 8: Exam Questions - 3
If we did manage to successfully get this live in October, would it be worth it?
  Sustainable long-term solution
  Ability to deliver business benefits
  Ability to deliver technical benefits
  Robust platform for future deployments

## Slide 9: Exam Questions - 4
What would you do differently in Release 2 and beyond?
  Establishment of metric driven requirements baseline under change control
  Utilisation of requirements driven strategy for the definition of strategy and plans
  Utilisation of a tool like Jira and Confluence as a ‘project management’ tool
  Establishment of formalised entry / exit gate driven lifecycle stages
  Establishment of a Project Configuration Management defined lifecycle
  Centralisation of issue and defect management processes
  Ends means driven approch
  Establishment of a Decommissioning workstream