## RAID
RAID Log
This document is used by Project Managers to track Risks, Assumptions, Issues and Dependencies.
This template is for personal and business use and may not be made publically available without the prior written consent of Project Smart.
Risks
Assumptions
Dependencies
Issues
Visit Website

## Risks
Project Name: Configuration Management
Risk Register
Last Reviewed: {date}
Events that will have a negative impact on your project if they occur. Risk refers to the combined likelihood the event will occur and the impact on the project if it does occur. If the likelihood of the event happening and impact to the project are both high, you identify the event as a serious risk. The log includes a description of each risk, analysis and a plan to manage it.
ID | Date Raised | Risk Description | Likelihood | Impact | Severity | Mitigation Plan | Owner | Status | Date Closed
1 | 2018-03-21 | No Quality Assurance or Standards Defined | 5 | 5 | 25 | Implimentation of Quality Release Gates into CM Process to identify key aspects | Jamie Martin | Open
2 | 2018-03-21 | Manual Controls of Configuration into M3 - Risk of copying errors | 3 | 3 | 9 | Identify method of automating delivery of M3 Configuration settings | Jamie Martin | Open
3 | 2018-03-21 | M3 Configuration is 'controlled' within Environment | 1 | 1 | 1 | None | Cari Spokes | Closed
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
Note on E5: Scoring: Low = 1 Medium = 3 High = 5
Note on F5: Scoring: Low = 1 Medium = 3 High = 5

## Assumptions
Project Name:
Assumptions
Last Reviewed: {date}
Any factors that you are assuming to be in place that will contribute to the successful result of your project. The log includes details of the assumption, the reason it is assumed and the action needed to confirm whether the assumption is valid.
ID | Date Raised | Assumption Description | Reason for Assumption | Action to Validate | Impact if Assumption Incorrect | Status
1
2
3
4
5
6
7
8
9
10

## Issues
Project Name: Configuration Management
Issues Register
Last Reviewed: {date}
Something that is going wrong on your project and needs to be managed. Failure to manage issues may result in a poor delivery or even failure. The log includes a description of each issue, the impact it is having, its seriousness and actions needed to contain and remove it.
ID | Date Raised | Issue Description | Impact Description | Impact | Priority | Mitigation Plan | Owner | Status
1 |  | No Configuration Management Plan | No configuration management plan exists for Momentum | Medium | High | Define Stratgey and Plan | Jamie Martin | Open
2 |  | No Configuration Management System | No central configuration management solution outside of sofware dev and integration | Low | High | Identify suitability of GIThub and use of tool set as part of HCL post DD | Jamie Martin | Open
3
4
5
6
7
8
9
10
Note on F5: Scoring: High Medium Low
Note on G5: Scoring: High Medium Low

## Dependencies
Project Name:
Dependencies
Last Reviewed: {date}
Any event or work that are either dependent on the result of your project, or your project will depend on. The log captures who you are dependent on, what they should deliver and when. It may also include who is dependent on you.
ID | Date Raised | Dependency Description | Location | Deliverables | Delivery Date | Importance | Status
1
2
3
4
5
6
7
8
9
10
Note on H5: Scoring: High Medium Low

## Data (hidden)
Status | Importance | Prioirty | Impact | Location | Risk Level
Open | High | High | High | Internal | 1
Closed | Medium | Medium | Medium | External | 3
| Low | Low | Low |  | 5